## Project Charter
Project Charter |  |  |  | Back to main page
Project Charter
Project Name |  |  |  |  | A formal document that authorizes the PM and Project team to start the project and execute the project tasks. Project charter is a short document usually 3-4 pages; it can be higher depending on the project.
Project Description |  | Sponsor | Signs the project charter, there may be more than one sponsor; All sponsor name should be included
Project Manager |  | Signature
Authority Level of the Project Manager |  | Date Approved |  |  | Developing Project Charter Process
Business Case | Explains why the project is happening
[6 empty] | Inputs (What do we need) | Business Case Document - Requiered to create business case and Assumtion logs There are 2 types of business documents - Business Case - Benefits Management Plan | Business Case - Generally 15-20 paged long - Created before project is chartered - Reviewed and updated during the PLC - Sponsor is responsible for creation - Absolutely necessary Contents of Business Case - Business Needs - Contribution to Key objectives - Strategic benefits and risks - High level constraints and assumptions | Benefits Management Plan - Sponsor is responsible for creation and maintenance - PM can suggest changes
Estimated Budget | [6 empty] | Agreements - Between organization and customer
[5 empty] | Project Charter (ITTO) |  | Assumtion log - Contains high level constraints
Project Objectives | [6 empty] | Organizational Process Assets - Requiered to create Agreements and Assumtion logs
[7 empty] | Enterprise Environmental Factors | Internal and External Factor - Stakeholder Expectations - Industry Standards - Legal Regulations - Politics within the organization
Project Approval Requirements | What approval is required and who approves them Final approval and WBS approval is given by the sponsor
[6 empty] | Tools and Techniques (What do we Use) | Expert Judgements - Consult with experts - Consult with Staff working in the organization
High level Product Description/Key Deliverables | [6 empty] | Data Gathering Methods - Brainstorming - Focus Groups - Interviews | Data Gathering method helps us to determine - Summary milestones - Key Stakehoilders - High Level assumptions and risks
Meetings - Projects Scuccess Criteria - High level requirements and milestones
Preassigned Resources | [6 empty] | Interpersonal and Team Skills - Meeting Management - Conflict Management - Facilitation
Key Stakeholders | [5 empty] | Outputs | Project Charter
Assumption Log
Stakeholder Requirements
High Level Description of the product |  |  |  |  | Important Notes
Detaled planning of project charter is not done during the initiating projects
High Level Assumptions
High Level Constraints
High Level Risks
Summary Milestones
Project Exit Criteria | In what condition the project will be aborted
Project Success Criteria

## Knowledge Areas
Integration Management
Scope Management | Project managers primary role is integration management; to ensure coordination between all other processes)
Schedule Management
Cost Management
Quality Management
Resource Management
Communications Management
Risk Management
Procurement Management
Stakeholder Management

## Definitions
Term | Definition | Mnemonic Terms/Details
Project | Temporary tasks that creates something unique and has deadlines. | A project has two characteristics It is Temporary and it creates something unique
Why Project is initiated | Market demand Customer request Business need Environmental considerations Legal requirements Social need Technological advancement | All of this generates business value
Program | Group of related projects is called proigram
Portfolio | Unrelated mix of program, projects or operations working towards same strategic goal
Operation | Repitative ongoing tasks producing same result
Processes | 49
Process Groups | 5 | Initiating
Planning
Executing
Monitoring
Controlling, closing
PMO Types and Tasks | Supporvive | Creates standards, procedures and other Project documents
| Controlling | Supports the project as well as have limited control over the project
| Directive | Direcctly manage the projects and is responsible for the projects. Authority level highest
Organizational Governance | Provides wih High level strategic goals of the gorganization
Project Governance | Provides the project team with policies, processes, decicion making models and tools to administer the project
Responsibilities of a PM | Is the one who manages the projects to add value to his organization by achieving project goals Communicates Coordinates Involes in the project from or before initiation Works until the project/even after the project Proactive, solves the problem Assists and develop the team Uses leadership team
Stakeholder | Anyone who is related to the project and who affects or are affected by the project
Project Sponsor/Initiator | The one who provides finances for the project Supports the project Prevents unnecessary changes May/may not be from the organization
Role of Project Sponsor/Initiator | Says what to do/how to do - Determines key milestones - takes part in development process - creates the project charter/delagates to PM - Signs project charter - Prioritizes constraints and manages high level risks - Guide planning efforts - Approves the PM plan - Ensures the project is managed within the budget - Monitors the progress against the baseline - Authorizes Change control board - Accepts deliverables formally
Role of Project Team | Prepare Project schedule, budget, constraints and project payments, reports -Suggest changes -Update the schedule and budget Monitor and control work on site May share some roles of PM
Role of functional/resource manager | Head of department and a subject matter expert - Manages resources - Motivates team - Suugest changes and a member of change control board - only one who identifies risks - May approve project schedule/PM plan
Project Managers Approval is required if it is a | Change request
Final report
Project Management Plan

## Organizational Structure and PM
Types of organization | Types | Details | PM Authority | PM's and PM admin, staff role | Resource availability | Advantages | Disadvantages
Organic/Simple |  | Often owner does most of the role | Least | Part-Time | Low to none | Easy to specialize in a spedific subject Resources are more centralized and easier to manage Team member works in different projects | Team members sense of belonging is less Difficult to develop
Functional |  |  | Least | Part-time | lowest |  |  | Functional
Multi-divisional |  | Less centrlized, divided based on geographic , product/service, program, portfolio, customer type E.g: Microsoft USA, india etc) | Less | Part-time | Each sector has their own resources |  |  |  | Executives
Matrix | Weak | If it is close to the functional structure |  | Part-time |  | PM has more authority hense maanges resources better Team members are not temporary Coordination and communication is better | Hard to manage, monitor and allocate resources Conflict becomes evident due to structure
| Balanced |  |  | Part-time |  |  |  | Head of Dept A | Head of Dept B | Head of Dept B
| Strong | If it is close to the project-oriented structure | Higher | Full-time
Virtual |  | Operates virtually. Core business to itself, other works are outsourced | Higher | Part-Time/full time |  |  |  | Dept A | Dept B | Dept C
PMO |  |  | Highest | Full-time | Highest | Sense of belonging is highest, better administration and better communication
Project-Oriented |  | Work groups are determined by the type of project | Highest | Full-time | Highest |  | Team members are project based so hard to specialize on a single subject | Project 1 | Project 1 | Project 1
Hybrid |  |  | Mixed | Mixed |  |  |  | Project 2 | Project 2 | Project 2
[8 empty] | Project 3 | Project 3 | Project 3
* In the exam, unless otherwise stated consider organization as strong matrix
Project oriented (Projectized) Organizations
Executives
[8 empty] | PM of Dept 1 | PM of Dept 2 | PM of Dept 3
[8 empty] | Dept of Project 1 | Dept of Project 2 | Dept of Project 3
[8 empty] | Project 1 | Project 2 | Project 3

## All Processes, groups and KA
Knowledge Areas | Process Groups
| Initiating | Planning | Executing | Monitoring and Controlling | Closing | Knowledge Areas
1. Project Integration Management | 1.1 Developing Project charter | 1.2 Developing Project Management Plan | 1.3 Directing and Managing project work | 1.5 Monitoring and controlling project work | 1.7 Closing the project
|  |  | 1.4 Managing Project Knowledge | 1.6 Performing integrated change control
2. Project Scope Management |  | 2.1 Planning Scope Management |  | 2.5 Validating Scope
2.2 Collecting Requirements
|  | 2.3 Defining Scope |  | 2.6 Controlling Scope
2.4 Creating the WBS
3. Project Schedule Management |  | 3.1 Planning Schedule Management |  |  | 3.6 Controlling the Schedule
3.2 Defining Project Activities
3.3 Sequencing Activities
3.4 Estimating Resources and Duration
3.5 Developing a Schedule
Project Cost Management |  | 1. Planning Cost Management |  |  | Controlling Costs
2. Estimating Costs
3. Determining a Budget
Project Quality Management |  | Planning Quality |  | Managing Quality | Controlling Quality
Project Resource Management |  | 1. Planning Resource Management |  | 1. Acquiring Resources | Controlling the Resources
|  | 2. Estimating Activity Resources |  | 2. Developing the Team
3. Managing the Team
Project Communications Management |  | Planning Communications Management |  | Managing Communications | Monitoring Communications
Project Risk Management |  | 1. Planning Risk Management |  | Implementing Risk Responses | Monitoring Risk
2. Identifying Risks
3. Performing Qualitative Risk Analysis
4. Performing Quantitative Risk Analysis
5. Planning Risk Responses
Project Procurement Management |  | Planning Procurement Management |  | Conducting Procurement | Controlling Procurement
Project Stakeholder Management |  | Identifying Stakeholders |  | Planning Stakeholder Management | Managing Stakeholder Engagement
Mnemonics
All Knowledge areas (IPQ SSS CC RR)
Note on B2: What is created during Initiating process - Project Charter - Assumption Log
Note on C3: Change management and configuaration management plan is created
Note on C9: Nikbs: How to manage & control schedule
Note on F9: Nikbs: Measuring schedule progress against the schedule baseline
Note on C10: Nikbs: Activitis involed in the schedule of project
Note on C11: Nikbs: Creation of project schedule network diagram. Logical relationship of activities and
Note on C12: Nikbs: Estimating techniques (e.g: One point/three point/parametric estimating)
Note on C13: Nikbs: Schedule network analysis, CPM calculations

## Integration Management
Project managers primary role is integration management; to ensure coordination between all other processes) |  |  | Back to main page
Considerations behind tailoring Project Integration Management processes | Project Life Cycle (Determine the pases)
Developing life cycle type (Predictive/Adaptive)
Maanagement Method (by considering organizational culture and size of project)
Knowledge
Change Management
Administrative needs (Preparing Executive reports and how often we should prepare those reports)
Lessons learned
Benefits reports
Develop Project Management Plan
Detailed Plans which integrates all other proceses, Iterative process
Initiating process: Developing Project Charter
Planning process: Developing Project Management Plan
Components of project management plan | Knowledge Areas | Subsidiary Management Plan
Project Life cycle (Plan driven/Change driven life cycle) | Integration Management | Change Management Plan + Configuaration Management Plan
Development Approach (Iterative/Agile/predictive/Hybrid model) | Scope Management | Scope Management Plan + Requirement Management Plan
Management reviews (How often) | Schedule Management | Schedule Management Plan
Performance Measurement Baseline (Given In Order) - Scope Baseline - Project Scope Statement - Work breakdown structure (WBS) - WBS dictionary - Schedule Baseline - Cost Baseline | Cost Management | Cost Management Plan
| Quality Management | Quality Management Plan
| Resource Management | Resource Management Plan
| Communications Management | Communications Management Plan
| Risk Management | Risk Management Plan
| Procurement Management | Procurement Management Plan
| Stakeholder Management | Stakeholder Management Plan
Change Management Plan - Explains how to deal with changes - Defines Change Control Procedures - If there are changes we have to do Change control | Template (Change Mangement) | Change Control System - Softwares, Reports, forms and procedures - Part of PMIS and Enterprise environmental factors
Configuaration Management Plan - Plans for tracking the change requests for a document and finding out the most recent version - Can be done by introducing a labeling system/naming convension |  | Configuaration Management system -Part of PMIS - Uses organizational tools, processes and procedures
ITTOs of Developing a Project Management Plan
Output | Project Management Plan
Input | Project Charter
Outputs of Other Knowledge area processes
Organizational Process Assets
Enterprise Environmental Factors
Tools and Techniques | Expert Judgement
Data Gathering Techniques
Interpersonal and Team Skills - Conflict Management - Facilitation - Meeting Management
Regular and Kick off Meetings (Key Parties in the meeting)
Important Notes
Project management plan should be formally approved by all the stakeholders In a kickoff meeting
Project management plan is not the sole source needed to manage the project. Project documents are also needed.
But project documents are not included in the project management plan
Some Project documents: Issue log, Project Schedule, Cost estimates, Assumption log, Quality report etc.
Project documents are not approved by the sponsor
Project documents are usually created by project managers with the help of a project team
Executing process: Direct and Manage Project Work
Manage and perform work as per project management plan - Manage the people Managing activities: Dealing with problems, trying to do the work economically, keeping stakeholders engaged - Hold and facilitate meetings (to better manage people and ensure coordination between stakeholders - Create deliverables (Anything that is created after the planning efforts) - Work performance data is collected - Issue log is created - Change Requests are created - Updates on Project management plan, project documents and organizational process assets are applied | Issue Log Template
ITTOs of Direct and Manage Project Work
Outputs | Deliverables
Work Performance Data
Issue Log
Change Requests
Project management plan updates
Project Document updates
Organizational Project Assets updates
Inputs | Project management plan
Project Document
Organizational Project Assets
Approved Change Requests
Enterprise environment factors
Tools and Techniques (What do we Use) | PMIS
Meetings
Expert Judgement
Important Notes
Work Flow so far
| Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Work
Business Documents >>>>>> | Project Charter | Project management plan | Project Work
Prepared By Sponsor | Prepared and Approved by sponsor (PM may help) | Prepared by PM and project team' approved by important parties
Executing process: Manage Project Knowledge
Deals with storing and sharing of historical knowledge
Project manager is responsible for managing the project knowledge (Both Information and knowledge management)
Stakeholders should be encouraged to interchange the knowledge
Stakeholders should not fear while providing knowledge they learned from mistakes
Two types of knowledge
Explicit Knowledge | Tacit Knowledge
Based on or concerned with true events and experiences | Feelings, emotions and abilities
Easy to express with words and/or numbers | Not easy
If you are managing explicit knowledge then you are doing information management | If you are managing Tacit knowledge then you are doing Knowledge management
Tools: Sofware/online applications, discussion forums, meetings, work shadowing, Activity observation
ITTOs of Manage Project Knowledge
Outputs | Lessions learned register
Organizational process assets revisions
Inputs | Project Management Plan | Project Documents
Lessions learned register
Project team assignments
Resource Breakdown structure
Stakeholder Register
Deliverables
Enterprise environmental factors
Organizational process assets
Tools and Techniques | Expert judgement
Information and Knowledge management
Interpersonal and team skills (Active listening, Facilitation, Leadership, Networking, Political awareness)
Important Notes
Monitoring and Controlling Process: Monitor and Control Project Work
Compares actual values against planned values
Monitoring and Controlling Process: Perform Integrated Change Control
Change Management Plan |  | Approved? | Updateing and replanning | Change request is only for the approved project
Want to make a change in a project?? | Place a change request | It will be evaluated by the change control board
|  | Not Approved | Don't apply the change | Document in the change log
Responsibilities of CCB - Impacts of change on other aspects needs to be evaluated
Schedule | Customer Satisfaction
Quality | Risks
Scope | Resource Motivation
How to deal with changes
Changes in
Project management plan
Project documents
Project Charter
Baselines
Company policies and procedures
Contracts
Statement of work
If affects those documents |  | If it doesn't affect those documents
Approval of CCB/Sponsor is required |  | Approval of Project Manager is enough
Change management plan
**If it is written in the change management plan that no matter whether it affects the documents or not you need approval of CCB/Sponsor you need to follow that
Dealing with changes procedure
Prevent the root causes of change
Still some problems can occur
point out works that need change request
investigate the impact of the change (KA based)
Create change request
Investigate impact on project
Determine the options | Approve change | Change Log Update | Update and replan | Communication/Configuaration management | Manage the revised project
Reject Change
Postpone Change
ITTOs of Perform Integrated Change Control
Outputs | Approved Change requests
Project Management plan updates
Project Revisions
Change log revisions
Inputs | Change Requests
| Change Management Plan | Project Management Plan
Configuaration Management Plan
Project Performance Measurement Baselines (Scope, Cost and Schedule Baselines)
| Project Documents - Basis of estimates - Requirements traceability Matrix - Risk report | ↓↑
Work Performance Report
Enterprise environmental factors
Organizational process assets
Tools and Techniques | Expert Judgement
Change Control tools (Softwares that support both change and configuaration management
Data Analysis - Cost-benefit analysis - Alternative Analysis
Decision making (Voting, Autocracy, Multicriteria decision analysis
Meeting
Important Notes
Project Manager is responsible for this process
Changes may happen verbally but it needs to be documented
Happens from initiating to closing
By doing proper risk management these changes can be reduced
Monitoring and Controlling Process: Close Project
A project can close either by
Completing | Terminating
Close the project/phase
before closing the project ask yourself
Requirement of the project are met?
Project management processes related to the project are met?
All of the contracts are closed? (with sellers and subcontractors)
Accecptance criteria met?
Final Customer Satisfaction -Customer may not be satisfied even after meeting all. So find out way of resolution | Gather and share final lession learned -Share it with organizations for future projects | Update Project Records | Make Final Payments | Create and Issue final Performance Report
↕ | ↓ | ↓ | ↓
Resolution | Update Processes, Procedures, Templates, Other Docs | Achieve Project Records | Finalize Cost Reports
↓
Customer satisfaction evaluation
Transfer the products of the project
Examine the Achievements of the Project
Complete the closing process
ITTOs of Closing the Project
Outputs | Final Report/Final performance report
Project document revisions (Including lessions learned register)
Organizational project assets revision
Handing of the final product/service
Inputs | Project charter
Project management plan
All project documents (Assumption log, Basis of estimates, change log, issue log, lessions learned register, Milestone list, Project communications, Quality control measurements, Quality reports, Requirements documentation, Risk register, Risk report)
Accepted deliverables and agreements
| Business documents (Business case, Benefits management plan) | Benefits Management Plan -Business document -created before project is chartered Reviewed and updated during PLC -Project Sponsor is responsible for Benefits Management Plan
Procurement documentations
Organizational process assets (Closure guidelines, Configuaration management knowledge base)
Tools and Techniques | Expert Judgement
Data Analysis (Document Analysis, Regression Analysis, Trend Analysis, Variance Analysis
Meetings
Agile considerations in the integration project management area
Team Members | Project Manager
Local domain members | Responsible for big picture by showing - Leadership - Collaborative environment
control of detailed planning of the project | Servant leader - Not a manager leading from outside, rather a team member having leadership
Decides integration of the plan
They are generalists
Historical Information, Processes, Procedures
Existing systems and company culture

## Scope Management
Scope | The work that we will do in the project |  |  | Back to main page
2 major Rules of Scope management | Do not do less than written in the scope | Scopes can be updated
Do not do more than written in the scope/gold plating
Types of scope | Product Scope | Features and functions - Part of project scope
| Project Scope | Includes Project work & Product scope
Scope Management: Planning Scope
In this process, we create plans to manage and control scope not the scope itself. This is also an iterative process. You may not have the project management plan/quality management plan in the first day which is an essential input for the process but it will affect Scope management plan and Requirements management plan after the creation
Two plans are created | Scope management plan | Major Output of the process - Decribe how to plan, execute and control Project Scope - Complete the project within desired scope - Create a detailed Project Scope Statement - Approve scope baseline - Produce how to create the WBS, not the WBS
| Requirements Management Plan | It is a component of Project Management Plan Includes information about indentifying, analyzing, documenting and managing the requirements
ITTOS of Planning Scope
Outputs | Scope management plan
Requirements Management Plan
Inputs | Project charter
| Quality Management Plan (What materials we will use (High quality/Low quality)) | Project Management Plan
Project life cycle description
Development Approach (e.g.: Waterfall/Iterative
Enterprise environment factors
Organizational process assets
Lessons learned register/Historical data from previous projects
Tools and Techniques | Expert Judgement
Meetings
Alternatives Analysis/Data Analysis
Scope Management: Collecting Requirements
determine the detailed requirements from all the stakeholders (Quality requirements/Requirements due to law,PMO requirements, Other organizational requirements )
Document and manage requirements
What requirements shouldn't be considered? | That are not aligned with the project objectives/business case written
ITTOS of Collecting requirements
Outputs | Requirements Document | All requirements should be clear and measurable Requirements needs to hava an acceptance criterion (How they will be validated) Verification is not done here
| Requirements Traceability Matrix | Tracking requirements and linking them to objectives
Inputs | Project charter
| Requirements Management Plan | Project Management Plan
Scope Management Plan
Stakeholder Enagagement Plan
| Assumption log | Project Documents
Stakeholder register
Lessons learned register/Historical data from previous projects
Business Case
Agreements
Enterprise Environmental factors
Organozational Project assets
Tools and Techniques | Expert Judgement
Meetings
Document Analysis/Data Analysis
Data Gathering (Brainstorming, Interviews/Expert interviews, Focus groups, Questionnaires and Surveys, Benchmarking
| Decision Making (Voting, Multicriteria Decision Analysis, Autocrating decision making | 3 ways of evaluating votes - Unanimity - Majority - Plurality
Data representation - Affinity diagram - Mind Mapping
Interpersonal and team skills - Nominal Group skills (Similar to brainstorming just with prioritized ideas) - Observation and conservations - Facilitated Workshops (Used for User stories, Joint application design/development (Software projects), Quality function deployment (Manufacturing Industry)
Context Diagram
Prototype
Scope Management: Defining scope
Detailed description of the deliverables/Scope and also determine the | Boundaries | Project Scope Statement
Assumptions
Acceptance criteria
Constraints
Required documents for project scope statement | Lessions Learned
Project Charter
Risk register
Project Scope Statement
Scope baseline | WBS Dictionary
WBS
ITTOS of Defining Scope
Outputs | Project Scope Statement
Revisions in Project documents - Requirements documentation - Requirements Traceability Matric - Assumption log - Stakeholder Register
Inputs | Project charter
Scope Management Plan
Assumption log
| Assumption log | Project Documents
Requirements documentation
Risks Register
Lessons learned register/Historical data from previous projects
Enterprise Environmental factors
Organozational Project assets
Tools and Techniques | Expert Judgement
Alternative Analysis/Data Analysis
Multicriteria decision Analysis (Decision Making Analysis)
Facilitation (Interpersonal and team skills )
Product Analysis -Value engeneering, systems analysis, Product breakdown, requirements analysis
Data representation - Affinity diagram - Mind Mapping
Context Diagram
Prototype
Scope Management: Creating WBS
Dividing the project into smaller managable groups and sub-groups to easily handle work-packages
We divide the work until - We can finish the work fast and easily - We can subcontract the work easily - We can make the realistic cost, schedule and scope estimation easily
A work package consists of activities
WBS numbering is helpful for finding the location of a work package in the WBS
Advantages | Better communication between stakeholders
Better understanding of works
Need for resources, cost and duration is checked
High quality work
Helps to see the big picture
Provides facilitation
Helps determining the risks
Decreases the number of changes
Project will be managed easily
Use of WBS | Determining and sequencing the activities
Creating the network diagram
Determining resources
Preparing and controlling schedule
Preparing and controlling budget
Identifying and managing the risks
Managing Quality
Conducting Procurements
Evaluating the change requests
Preventing the scope creep (Uncontrolled growth of the scope of the project)
Providing communications
Why do we use WBS dictionary | To prevent scope creep
It is a iterative process so we will not have everything together
Authorizing works (As a part of Work authorization system)
Scope baseline | WBS
WBS dictionary
Project Scope Statement
ITTOS of Creating WBS
Outputs | WBS | Scope Baseline
WBS dictionary
| Revisions in - Requirements Documentation - Assumption Log | Project Documents
Inputs | Scope Management Plan | Project Management Plan
Project Scope Statement
Enterprise Environmental factors
Organizational Project assets
Tools and Techniques | Expert Judgement
Decomposition
Important Notes
All projects regardless of their size should have WBS
WBS creation has positive effects on on the project
All of the deliverables are defined at WBS
Dependencies of the activities, tasks or the work packages are not defined in WBS
Scope Management: Validating Scope
Minimizing Mistake
Big Picture
Scope Management Plan
↓
Requirements are defined
↓
| Project Scope statement is created | Scope Baseline
↓
WBS and WBS dictionary are created
↓
Project management plan is approved
↓
| Deliverables are produced | Controlling Scope
↓
Quality Control (Internally verified deliverables)
↓
Validate Scope (External/Customer)
↓
Project work is completed
↓
Final Acceptance of the product
Purpose of Validating Scope | Obtaining interim validation from customer/sponsor
Planned meetings are held for formal validation
QC procedures should be performed internally before sending the deliverable for validation. This process is known as verified deliverables.
If the deliverable cannot pass the QC review, change request is created
Work performance information is produced
ITTOS of Validating Scope
Outputs | Accepted Deliverables
Change requests
Work Performance Information
| Revisions in - Requirements Documentation - Requirements Traceability Matrix - Lessons Learned register | Project Documents
Inputs | Scope Management Plan | Project Management Plan
Requirements Management Plan
Scope baseline
| Requirements documentation | Project Documents
Requirements Traceability Matrix
Lessons learned register
Verified Deliverables
Quality reports
Work Performance data
Tools and Techniques | Inspection (Internal)/ Validating/Testing/Reviewing/Walk-Throughs
Decision Making Analysis (Voting)
Scope Management: Controlling Scope
Here we measure the actual work against the scope
To control scope | Scope baseline needs to be realistic
Project work needs to be started
Controlling the scope may cause changes in the PMP and project documents
Unnecessary changes/scope creep are prevented by controlling the scope
Project work
| Control Scope | Deliverable 1 | QC | Validate Scope
ITTOS of Controlling Scope
Outputs | Work Performance Information
Change requests
Revisions/updates in - Scope Management Plan - Scope Baseline - Schedule Baseline - Cost Baseline - Performance measurement baseline - Requirements Documentation - Requirements Traceability Matrix - Lessons Learned register
Inputs | Scope Management Plan
Requirements Management Plan
Scope baseline
| Requirements documentation | Documents needed to create requirements documents - Scope Management Plan - Assumption log - Project charter
| Requirements Traceability Matrix | (Provides priorities of the requirements Link requirements to the project needs and objectives
Performance measurement baseline
lesson learned register
Work performance data
Organizational Process Assets
Tools and Techniques | Data Analysis (Variance Analysis, Trend Analysis)
Tailoring Scope management considerations | Existing knowledge and requirements management systems
Guidelines, policies and procedures related to validation and control
Development approach of organization
Organizational governance
Number of unstable requirements
Not Verified?
Initiiate change req.
Integrated
Change
Control
Approved

## Schedule Management
Back to main page
Schedule Management: Plan Schedule Management
How we are going to manage the schedule
Activities | Scheduling software is determined | Schedule Management Plan
Scheduling metrics are determined (Days/weeks
Scheduling tolerance/control thresholds
Scheduling approach
Accuracy level
Controlling and managing variances; changing and revisions
If it is an adaptive environment the length of releases and iterations
Format of reports
ITTOS of Planning Schedule management
Outputs | Schedule Management Plan
Inputs | Project Charter
| Scope Management Plan | Project Management Plan
Development Approach (Adaptive/Predictive)
Enterprise Environmental factors (Scheduling tools, Culture, Availability/accesibility of resources)
Organizational Process Assets
Tools and Techniques | Expert Judgement
Data Analysis (Alternative analysis)
Meetings
Schedule Management: Define Project Activities
Here we define activities by decomposing the work packages
Some milestones/important achievements are determined
Activity and task are not the same; activity is composed of multiple tasks
ITTOS of Defining Project activities
Outputs | Activity List
Activity Attributes
Milestone List
Change Requests
| Updates/revisons in - Schedule baseline - Scope baseline | Project Management Plan
Inputs | Schedule Management Plan
Scope Baseline
Enterprise Environmental factors (Scheduling tools, Culture, databases, templates)
Organizational Process Assets
Tools and Techniques | Expert Judgement
Decomposition
Meetings
Rolling wave planning (. It is a progressive elaboration method. Making an initial planning with known components in detail and unknown components in high-level, project work keeps going and this can be changes later
Schedule Management: Sequencing the Activities
Network diagram/Schedule network diagram/Activity network diagram methods | Precedence Diagramming Method (PDM)/Activity on Node AoN ***
Arrow Diagramming method (ADM) Activity on Arrow AoA
Graphical evaluation and review technique (GERT)
Precedence Diagramming Method (PDM)/Activity on Node AoN ***
Dependency Type (How will you choose which PDM to use | Hard Logic (Mandatory Dependancy) | Can not build a second floor without completing the ground floor | PM team
| Soft Logic (Discretionary/Preferred/Preferencial Dependancy) | Not a must case, you can build doors and windows together or one after another
| Exterenal Dependency | Without DGDA permission you can not launvch product | PM/PM team can help
| Internal Dependency | Vital team member is on leave
Drawing a network diagram from given activity list
Activity | Predecessor
A
B | A
C | B
D | B
E | A
F | D
G | D, E
H | C
I | H, F, G
Activity | Successor
A | B, D, E
B | C
C | H, I
D | F
E | G
F | I
G | I
H
I
Why Network diagram? | Provides better understanding about the activity and schedule
ITTOS of Sequencing the Activities
Outputs | Revisions/Updates in Activity List Activity attributes Milestone List Assumption Log | Project Documents
Inputs | Schedule Management Plan | Project Management plan
Scope Baseline
| Activity lists and Activity attributes | Project documents
Milestone list and assumption log
Enterprose environment factors (Organization authorization system, industry standards)
Organizational process assets
Tools and Techniques | Precedence diagramming method
Dependency determination and integration
Leads and lags
PMIS (Scheduling softwares)
Schedule Management: Estimating resources and activity duration
Same techniques are used while estimating duration and cost of the activities
Estimating techniques | One point estimating | One estimate for each activity Estimation is based on historical data/expert judgement/guess | Example: It will take 10 days to build a software
| Analogous/Top down estimating | Provides fast result but Less accourate than parametric,/three point estimation No calculation; Historical information is used by using similarity to estimate project/invidual tasks cost/duration | A previous project was completed in 5 months, this year in another place we
Bottom -Up Estimating
| Parametric Estimating | Calculation is done on standarfd metric, industry movements, other sources and historical info. Results are more accurate Two methods are used to do the calculation - Regression analysis (scatter diagram): two variables from previous projects/other sources and find dependency of these variables with current data - Learning curve: By doing a task multiple times that tasks completion times reduces Heuristics are mental strategies to make estimation that are used here as well
| Three point estimating | Provides most realistic duaration and cost estimation Three types Optimistic Estimation (O, tO or cO Most likely estimation (M, tM, cM) Pessimistic Estimation (P,tP, cP)
Triangular distribution/Simple/straight distribution Expected activity duration /cost = (P+M+O)/3
Beta Distribution/Weighted Average/PERT(Program evaluation and review technique)/Bell shape curve There are two formulas Expected activity duration/cost = (P+4M+O)/6 Standard Deviation = (P-O)/6
This is not a calculation only process there are other factors as well
Padding | When you talk with experts to find about about duartions of tasks the experts sometime add some extra dates to due to different risks involved. This is called padding Adding extra time/cost on the estimation Padding is not allowed PM is responsible to make a relistic schedule Three point estimating can help solve this problem. Take three dates or costs to negate padding (Optimistic, Pessimistic, Most-likely
Law of diminishing returns | After a certain point, no matter how much you increase input, productivity will not increase
Experience, capability and number of resources
Technology to be used
Team motivation
Role of PM in estimating duration
Ensures team has enough information for estimating work
Motivates team to provide realistic and refined estimates
Determines the necessary techniques to prevent padding
Checks if the estimations are reliable and logical
Determuines the contingency reserves
Ensures the assumptions are documented
ITTOS of Estimate resources and activity duration
Outputs | Duration Estimates
Basis of estimates -Constraints, Assumptions and risks -Trust level of the estimates - Range estimation for the estimates (+- 5%)
| Revisions in Activity attributes Assumption log Lessions Learned refister | Project documents
Inputs | Schedule Management Plan | Project Management Plan
Scope Baseline
| Activity lists and Activity attributes | Project documents
Milestone list and assumption log
Lessions learned register
Project team Assignments
Resource breakdown structures
Resource Calenders
Resource requirements
Risk registers
Enterprise environmental factors
Organizational process assets
Tools and Techniques | Expert judgement
Estimating techniques
Data analysis methods (Alternative analysis, reserve analysis etc) Two types of reserves - Predictable risks (Calculate individual schedule reserve to find out contingency reserve risks)if we add times over this it will be management reserve)
Decision making technique (Voting) Voting techniques Plan - driven projects : Majority, Plurality, Unanimity Change-driven projects: Fist to five/Fist of five
Meetings
Important Notes
WBS is required for more precise estimates
Management plans (Schedule and cost is required
Duration and cost estimates are related to each other
Padding is not allowed
Risks should be reflected
Persons related to the work should be involved in the estimation works
After PMP approval change request is created for changing an estimate
Estimation is easier and more precise dor smaller work components
PM is responsible for the correctness of the estimates
Schedule Management: Developing Schedule
Develop Schedule process | overview
Schedule management plan is created | Plan Schedule management
↓
Activities are defined | Define activities
↓
Activities are sequenced | Sequence Activities
↓
Activity durations are estimated | Estimate activity durations
↓
Scheduling calculations | Develop schedules
Schedule netwwork analysis
Critical path method (CPM) | Method of determining critical path/paths of a network diagram
Critical Path | Path in which any delay in activities of critical path will delay total project
Float/Slack | Delayed tolerance of any activity For critical path float = 0 Activities that are other than in the critical path has some delaying tolerance
Three types of float
Total float | Activities delay tolerance without affecting the toal project duration
Free Float | Activities delay tolerance without affecting the successor activities early start date
Project Float | Activities delay tolerance without affecting the target project duration given by sponsor/customer/PM
Critical Path method calculations
Forward pass
ES: For first activity 1 For others EF+1 | Will be determined beforehand/given | (ES+DURATION)-1
Early Start (ES) | Duration | Early Finish (EF)
Activity Name
Late Start (LS) | Float/Total Float | Late finish (LF)
LS = (LF-Duration) + 1 | Total float : LS - ES or LF - EF | For last activity LF = EF of previous task For others LF = LS -1
Backward pass
ES: Earliest time that an activity can start | EF: Earliest time that an activity can finish
LS: Latest time an activity can start | LF: Latest time an activity can finish
Note: For forward pass when two activity merges to a same activity (example: C - E/D-E) we should go with activity that has higher EF number For backward pass when two activity merges into a same activity (example: B-A/D-A) we should go with activity that has lower LS number
Two Calculation method:
Method 1: Start of day notation | PMBOK approves
Method 2: End of day notation
Example
Total float shows the risk tolerance of an activity/path
Number of critical path ↑ | Risk ↑
Number of near critical paths ↑ | Risk ↑
float ↑ | Risk ↓
Number of activities in network diagram ↑ | Risk ↑
Free Float =[ES(Successor) - EF(Current)] -1
Schedule compressiom | When sumone says after giving them project duration that you have to do that in shorter time
After developing schedule look for better options
Two techniques are used to reduce the project duration
Fast tracking
Project Duration 9 days
By fast tracking we can reduce the time into 7 days
Crashing
By increasing Manpower/resources we can reduce project duration
Disadvantages | Fast tracking | Crashing
| Weak Communication | Increased Risk (Sometimes)
| Re-work | Increased cost (always)
Increased Risk (Always)
Increased cost (sometimes)
Monte carlo analysis
Resource Optimization
Agile Release Planning
start
A
B
C
1
2
2
Activity A
1
0
2
3
3
5
Activity B
3
0
5
3
5
7
Activity D
5
2
9
6
4
9
Activity C
6
0
9
10
1
10
Activity E
10
0
10
11
3
13
Activity F
11
0
13
5
3
7
Activity B
5
0
7
START
10
0
9
FINISH
10
0
9
1
4
4
Activity A
0
0
4
8
2
9
Activity C
8
0
9
5
3
7
Activity B
5
0
7
START
10
0
9
FINISH
10
0
9
1
4
4
Activity A
0
0
4
8
2
9
Activity C
8
0
9

## Activity Attributes Template
Activity Attributes
Description of Activity
Id Number
Assigned work package
Resource requirements
Predecessors and successors
Constratints and assumptions
Deadlines

## Sheet2
Situation | Action | Result
Asked to implement a queueing system to efficiently manage customer flow on world arthritis day | Set up meeting with cross-functional departments and leadership team Communicated effectively regarding the expectation and deliverables | Reduced Client queue by 12%
Needed to attend a clients scheduling requirements at the same time management tasked me to prepare reports for board meeting | Approached client regarding the situation and asked whether it'd be okay if I take 1 more hour to attend his issue, apologised for the inconvenience. After clients approval, sent request to IT team for raw meeting data, at the same time contacted the respective sales colleague to inform about the client requirements Convinced him to start processing Clients requirements. | Generated errorfree report Fulfilled customer requirements Business increased over last month 28%
Client was furious regarding his bill increase with fine and wanted a detailed explanation | Let client vent out, Showed empathy and explained the reasons behind the increase, why the fine was charged and how it could be avoided Since customer had a good paying record waived the fine as per organizational protocol' | Customer was satisfied, even apologized for the behavior and
Management wanted to get rid of paper based approval system for new products | Developed directions to replacing paper based

## Change Management Template
Change Management Plan | [5 empty] | Back to Integration Management
Project Name/ID:
Change Management Approach: |  |  | Defining general attitude against changes
Definitions of Change
Change | Scope
Schedule
Budget
Project Documents
Change Control Board
** People who wil approve/reject changes **
Name |  | Position |  | Responsibility | Authority
Change Control Process
Change Request | Submital
Tracking
Review
Disposition
Important Notes
Defines change control procedures
For any changes do the change control which is logging changes in Change management sheed and geeting approval from the board
Some companies have software, reports, forms and procedures for change control

## Issue Log Template
Issue Log | [8 empty] | Back to Integration Management
Issue # | Issue Description | Impact level | Report date | Reported by | Responsible | Due date | Status | Notes
1 | Client is insisting for work not covered within the scope | High | 2023-02-10 | A | D | 2023-07-31 | Closed
2 | Key project team member is on leave | Medium | 2023-02-11 | B | E | 2023-08-01 | Open | Waiting for management approval
3 | User name alliows HTML extension | High | 2023-02-12 | C | F | 2023-08-02 | Closed

## Lessions Learned register
Lessions Learned Register |  |  |  |  | Back to Integration Management
Technical
Date | Submitted by | Experience Type | Description of the problem/situation | Proposed solution
Management
Date | Submitted by | Experience Type | Description of the problem/situation | Proposed solution
Project Management
Date | Submitted by | Experience Type | Description of the problem/situation | Proposed solution

## Benefits Management Plan
Benefits Management Plan Policy |  | Back to Integration Management
Introduction | Description of the benefits
Roles and Responsibilities | Who owns the benefits
Information Management | When will the benefits deliver
Assurance | Benefit measuring method, Risks and assumptions while determining the benefits
Budget
Schedule
Interfaces
Procedure
Quantify
Value
Plan Benefits Realisation
Realise Benefits
What is Benefits Management Plan
Benefits Management Plan -Business document -created before project is chartered Reviewed and updated during PLC -Project Sponsor is responsible for Benefits Management Plan

## Requirements Traceability Matri
Project Name: | [11 empty] | Back to Scope Management
Preparation Date:
Requirements Traceability Matrix
ID | WBS Code | Requirements Type | Requirement | Priority | Source | Department | Business Justification/Need | Test Strategy | Tested in | Inplemented In | Status

## Affinity Diagram, Mind Mapping
Project Name: | [5 empty] | Back to Scope Management
Preparation Date:
Affinity Diagram (For collect requirements process)
Matrial | Design | Safety | PMO | Appearance
Requirement 1 | Requirement 1 | Requirement 1 | Requirement 1 | Requirement 1
Requirement 2 | Requirement 2 | Requirement 2 | Requirement 2 | Requirement 2
Requirement 3 | Requirement 3 | Requirement 3 | Requirement 3 | Requirement 3
| Requirement 4 | Requirement 4 | Requirement 4 | Requirement 4
| Requirement 5 | Requirement 5 |  | Requirement 5
| Newly Identified requirement | Requirement 6 |  | Requirement 6
| Newly Identified requirement | Requirement 7 |  | Requirement 7
|  | Requirement 8 |  | Newly Identified requirement
|  | Requirement 9 |  | Newly Identified requirement
Newly Identified requirement
Mind Mapping
Requirement 4
[5 empty] | Organized Requirements | Requirement 5
Requirement 1 | [5 empty] | Newly Identified requirement
Requirement 2 | [5 empty] | Newly Identified requirement
Requirement 3 |  |  |  | Requirement 1
| PMO |  | Safety | Requirement 2
Requirement 3
|  | Project |  |  |  | Safety Laws
Requirement 6
Requirement 7
Newly Identified requirement
|  |  | Design |  |  |  | Newly Identified requirement
Requirement 1
Requirement 2
Requirement 3
| Appearance |  |  | Requirement 4
Requirement 1 |  |  |  | Requirement 5
Requirement 2 |  |  |  | Newly Identified requirement
Newly Identified requirement
Color |  | Material
Requirement 3 |  | Requirement 1
Requirement 4 |  | Requirement 2
Newly Identified requirement |  | Requirement 3
Logos
Requirement 5
Requirement 6
Newly Identified requirement

## Context diagram
Back to Scope Management
Website Users
|  | Sign-in |  | information
Ad slots
Invoices, Financial data
Google Ads |  |  | Website |  | Accountants
| Income |  |  | Tax reports, financial reports
|  | Blog Content |  | $100/writing
Bloggers

## WBS dictionary
Project Name: |  | Last Updated: | Back to Scope Management
Work Packages Name/ID: |  | Approved by:
Control Account: | Provides high level control of constraints (Schedule, Cost and Scope)
Responsible Name: |  | Approval Date:
WBS Dictionary
Description of the work package:
Included work:
Criteria for Approval:
Constraints and Assumptions
Budget:
Assigned Resources
Technical Sources:
Quality Metrics:
Risks:
Start Date/Duration/Due Date:
Milestones:
Predecessors/Successors:

## Sheet1
| Sat | Sun | Mon | Tue | Wed | Thu | Fri
Week 1 | C
Week 2
Week 3
Week 4
| 18.79 | 1315.3
20
42
2329.96
1600/1700 | 1800
8 MONTH |  |  |  |  | 0.26667
1 Yr
950 |  | no have
150 |  | no have
58 |  | no have
350 |  | no have
no have
2000 | 1200 | no have
800 |  | no have
no have
no have
| 70 | no have

## Sheet4
rocess Groups | Initiating | Planning | Executing | Monitoring | Controlling, closing
Project Integration Management
Project Scope Management
Project Schedule Management
Project Cost Management
Project Quality Management
Project Resource Management
Project Communications Management
Project Risk Management
Project Procurement Management
Project Stakeholder Management